## api
Role Schema API
HTTP method | router | endpoint | function
POST | /roles | /create | Create a new role
User Schema API
HTTP method | router | endpoint | function
POST | /users | /register | register
POST | /users | /login | login
GET | /users |  | Get all users
GET | /users | /:UserID | Get all user by id
DELETE | /users | /:UserID | delete
board Schema API
HTTP method | router | endpoint | function
POST | /board
Project Schema API
HTTP method | router | endpoint | function
POST | /Projects |  | Create a new project
GET | /Projects |  | Get all Project
GET | /Projects | /:id | Get spacific project
PUT | /Projects | /:id | Update a specific project
DELETE | /Projects | /:id | Delete a specific project
Ticket Schema API
HTTP method | router | endpoint | function
POST | /projects/:projectId/ | /tickets | create tickets
GET | /projects/:projectId/ | /tickets | Get all tickets for a specific project
GET | /tickets | /:ticketId | Get ticket by ID
DELETE | /tickets | /:ticketId | Delete a specific ticket
PUT | /tickets | /:ticketId | Update a specific ticket
Card (Subtask) Schema API
HTTP method | router | endpoint | function
POST | /tickets/:ticketId | /cards | Create a new card (subtask)
GET | /tickets/:ticketId | /cards | Get all cards for a specific ticket
GET | /cards | /:cardId | Get a card (subtask) by ID
PUT | /cards | /:cardId | Update a specific card
DELETE | /cards | /:cardId | Delete a specific card
Activity Schema API
HTTP method | router | endpoint | function
POST | /cards/:cardId | /activities | Create a new activity
GET | /cards/:cardId | /activities | Get all activities for a specific card
PUT | /activities | /:activityId | Update a specific activity
DELETE | /activities | /:activityId | Delete a specific activity

## timeLine
Initial Setup and Database Schema
Day 1 | 1 | set up the project repository (Git).
| 2 | Create the basic folder structure for the backend (Node.js/Express).
| 3 | Initialize the database schema (MongoDB):
| 4 | Define schemas: Role, User, Project, Ticket, Card, and Activity.
REST API & User Management
Day 2 6-10-2024 | 1 | Set up REST API routes for User and Role schemas.
| 2 | Implement user authentication (JWT) in the backend.
| 3 | Set up role-based access control for admin features.
| 4 | Test User and Role API routes using Postman or Insomnia.
Project & Ticket APIs
Day 3 7-10-2024 | 1 | Set up API routes for Project and Ticket schemas in the backend.
| 2 | Implement notification feature in the backend (endpoints for sending and retrieving notifications).
| 3 | Set up API routes for Card and Activity schemas in the backend.
Day 4 8-10-2024 | 1 | check backend
User Management Frontend
Day 5 9-10-2024 | 1 | Create the basic folder structure for the frontend (React).
| 2 | Implement user registration and login functionality in the frontend.
| 3 | Create forms for adding and listing users and roles.
| 4 | Connect frontend forms to backend APIs.
Project, Ticket, and Card Management
Day 6 10-10-2024 | 1 | Implement frontend for creating and managing projects and tickets.
| 2 | Connect the frontend to the backend for project and ticket management.
| 3 | Implement frontend for creating and managing cards (subtasks) within tickets.
| 4 | Implement logging activities (comments, status changes) for cards.
UI Enhancements & Testing
Day 7 11-10-2024 | 1 | Implement notification display in the frontend.
| 2 | Integrate a drag-and-drop library (e.g., React Beautiful DnD) for cards and tickets.
| 3 | Add a light-dark mode toggle feature in the frontend.
| 4 | Implement favorite project functionality (mark/unmark projects as favorites).
| 5 | Perform end-to-end testing of all functionalities.
Day 8 12-10-2024 | 1 | check All Project
Extra tasks or polish (as needed)
Additional Features to Implement | 1 | Fix any bugs or issues encountered during testing.
| 2 | Polish the UI for a user-friendly experience.
| 3 | Finalize light-dark mode and favorite project features.
| 4 | Prepare a presentation or demo of the completed project.
| 1 | Light-Dark Mode:
Create a toggle switch for light/dark mode in the UI.
Use local storage to remember user preferences.
| 2 | Favorite Projects:
Add a "favorite" button to projects.
Implement API endpoints to handle marking/unmarking projects as favorites.